## Summary
BPM Platform — Unified Requirement Register
Source: docs/status/requirement_status.yaml (2026-06-14) + release records (EXP-3xx/4xx/601) + addon-2 borrowing backlog
Generated 2026-06-26. Status legend below. "All Requirements" sheet is the full list sorted by implementation order.
HEADLINE
Existing scope is essentially complete: of 315 tracked requirements, 307 are RELEASED. Only 8 remain open — all in the
Schema-Per-Tenant Migration / Epic 5 cutover (implemented or tested, awaiting final release back-fill) plus ISS-202.
The borrowing backlog (BRW-*, 20 items) is net-new; most backend borrows are already shipped under EXP-* (see notes).
STATUS (tracked requirements) |  |  | LEGEND
RELEASED | 307 |  | RELEASED | Merged to main, tested, released
IMPLEMENTED | 4 |  | TESTED | Tests pass; not yet released
TESTED | 1 |  | IMPLEMENTED | Code complete; tests/release pending
PENDING | 3 |  | PENDING | Not yet implemented
TOTAL | 315 |  | VERIFY | Borrow: confirm current state before building
|  |  | LIKELY/MOSTLY DONE | Borrow likely satisfied by shipped EXP-*
OPEN ITEMS (not released) — see "Action Items" sheet |  |  | NOT STARTED | Borrow: net-new work
ISS-501 | IMPLEMENTED | Resolve read/write authority from storage_mode
ISS-502 | IMPLEMENTED | SPT cutover transaction flips storage_mode after verified copy
ISS-503 | IMPLEMENTED | Remove legacy tenant_id/RLS predicates (SPT-03)
ISS-504 | IMPLEMENTED | Reconcile schema + per-tenant migration tracking (SPT-04)
ISS-202 | TESTED | Two-phase all-or-nothing variable merge
SPT-02 | PENDING | Data migration — copy rows into tenant schemas and remove RLS
SPT-03 | PENDING | Remove legacy bpm.tenant_id session variable and tenant_id predicates
SPT-04 | PENDING | Test suite update and ADP-12 regression

## All Requirements
# | Stage | ID | Title | Priority | Status | Implemented In
1 | 1 | DB-01 | Schema initialisation | MUST | RELEASED | src/db/migrations.zig
2 | 1 | DB-02 | Connection pooling | MUST | RELEASED | src/db/pool.zig
3 | 1 | DB-03 | Transactional integrity | MUST | RELEASED | src/db/pool.zig; src/db/migrations.zig
4 | 1 | DB-04 | Health check query | MUST | RELEASED | src/db/pool.zig
5 | 1 | ES-01 | Append event | MUST | RELEASED | src/event_store/store.zig
6 | 1 | ES-02 | Ordered read | MUST | RELEASED | src/event_store/store.zig
7 | 1 | ES-03 | Event idempotency | MUST | RELEASED | src/event_store/store.zig
8 | 1 | ES-04 | Global event stream | MUST | RELEASED | src/event_store/store.zig
9 | 1 | ES-05 | Event type registry | MUST | RELEASED | src/event_store/registry.zig
10 | 1 | ES-06 | Point-in-time query | MUST | RELEASED | src/event_store/store.zig
11 | 1 | ES-07 | Retention policy | SHOULD | RELEASED | src/event_store/store.zig
12 | 1 | ES-08 | Event metadata | SHOULD | RELEASED | src/event_store/store.zig
13 | 2 | PD-01 | Create definition | MUST | RELEASED | src/definition/graph.zig; src/definition/store.zig
14 | 2 | PD-02 | Graph validation | MUST | RELEASED | src/definition/graph.zig; src/definition/store.zig
15 | 2 | PD-03 | Version management | MUST | RELEASED | src/definition/store.zig
16 | 2 | PD-04 | Definition lifecycle | MUST | RELEASED | src/definition/store.zig; src/api/routes/definitions.zig
17 | 2 | PD-05 | Node types | MUST | RELEASED | src/definition/graph.zig
18 | 2 | PD-06 | Edge conditions | MUST | RELEASED | src/definition/graph.zig
19 | 2 | PD-07 | Definition retrieval | MUST | RELEASED | src/definition/store.zig; src/api/routes/definitions.zig; migrations/014_definition_stage.sql
20 | 2 | PD-08 | Definition snapshot | MUST | RELEASED | src/definition/snapshot.zig
21 | 2 | PD-09 | Definition import/export | SHOULD | RELEASED | src/definition/export_import.zig; src/api/routes/definitions.zig
22 | 2 | PD-10 | Definition search | COULD | RELEASED | src/definition/store.zig; src/api/routes/definitions.zig
23 | 3 | EE-01 | Start instance | MUST | RELEASED | src/definition/snapshot.zig; src/definition/store.zig; migrations/005_instances.sql; src/engine/instance.zig; src/api/routes/instances.zig; tests/integration/ee01_start_instance_test.zig
24 | 3 | EE-02 | Pure transition function | MUST | RELEASED | src/engine/transition.zig; src/main.zig; tests/unit/engine_test.zig
25 | 3 | EE-03 | Task activation | MUST | RELEASED | src/engine/transition.zig; src/engine/instance.zig; migrations/005_instances.sql; src/tasks/store.zig; src/api/routes/tasks.zig; src/main.zig; src/bpm.zig; tests/unit/test_engine_apply.zig; tests/unit/test_tasks_store.zig; tests/unit/test_tasks_api.zig
26 | 3 | EE-04 | Complete task | MUST | RELEASED | src/tasks/store.zig; src/engine/instance.zig; src/api/routes/tasks.zig
27 | 3 | EE-05 | Exclusive gateway | MUST | RELEASED | src/engine/transition.zig; vendor/cel/cel.zig
28 | 3 | EE-06 | Parallel gateway (split) | MUST | RELEASED | src/engine/transition.zig
29 | 3 | EE-07 | Parallel gateway (join) | MUST | RELEASED | src/engine/transition.zig
30 | 3 | EE-08 | Instance cancellation | MUST | RELEASED | src/engine/instance.zig
31 | 3 | EE-09 | Variable scoping | MUST | RELEASED | src/engine/transition.zig; src/engine/instance.zig; src/bpm.zig; src/tools/json_schema.zig; src/api/routes/tasks.zig; tests/unit/test_ee09_merge_variables.zig; tests/integration/ee09_merge_variables_test.zig; build.zig
32 | 3 | EE-10 | Execution error handling | MUST | RELEASED | src/engine/instance.zig
33 | 3 | EE-11 | State reconstruction | MUST | RELEASED | src/engine/transition.zig; src/engine/instance.zig; src/event_store/store.zig; src/bpm.zig; migrations/003_event_archive.sql; src/engine/reconstruction.zig; src/api/routes/instances.zig; src/main.zig; tests/unit/reconstruction_test.zig
34 | 3 | EE-12 | Concurrent instance safety | MUST | RELEASED | src/engine/instance.zig; src/api/routes/tasks.zig
35 | 4 | API-01 | REST conventions | MUST | RELEASED | src/api/errors.zig; src/api/middleware/content_type.zig; src/api/response.zig
36 | 4 | API-02 | Process definition CRUD | MUST | RELEASED | src/api/routes/definitions.zig
37 | 4 | API-03 | Instance management | MUST | RELEASED | src/api/routes/instances.zig; src/instance/store.zig
38 | 4 | API-04 | Task operations | MUST | RELEASED | src/api/routes/tasks.zig
39 | 4 | API-05 | History endpoint | MUST | RELEASED | src/api/routes/instances.zig; src/event_store/store.zig
40 | 4 | API-06 | Pagination | MUST | RELEASED | src/api/pagination.zig
41 | 4 | API-07 | Input validation | MUST | RELEASED | src/api/validation.zig; src/api/middleware/validate.zig
42 | 4 | API-08 | Bearer token auth | MUST | RELEASED | src/api/middleware/auth.zig; src/api/errors.zig
43 | 4 | API-09 | Request tracing | MUST | RELEASED | src/api/middleware/trace.zig; src/api/trace_context.zig; src/obs/logger.zig; src/api/errors.zig
44 | 4 | API-10 | Rate limiting | SHOULD | RELEASED | src/api/middleware/rate_limit.zig; src/api/middleware/auth.zig; src/api/errors.zig; src/main.zig; src/api/api_mod.zig
45 | 4 | API-11 | OpenAPI specification | SHOULD | RELEASED | src/api/openapi/mod.zig; src/api/openapi/model.zig; src/api/openapi/path_registry.zig; src/api/openapi/schema_registry.zig; src/api/openapi/version_source.zig; src/api/openapi/builder.zig; src/api/openapi/serialize.zig; src/api/routes/openapi.zig; src/api/api_mod.zig; src/main.zig; src/tools/openapi_gen.zig; build.zig
46 | 4 | API-12 | Health endpoints | MUST | RELEASED | src/api/routes/health.zig; src/api/health/readiness.zig; src/api/health/subsystems.zig; src/api/openapi/builder.zig; src/api/routes/openapi.zig; src/main.zig
47 | 5 | IDN-01 | User registry | MUST | RELEASED | src/identity/registry.zig; src/identity/service.zig; src/api/routes/identity.zig; src/api/middleware/auth.zig; src/main.zig; migrations/017_identity_user_registry.sql
48 | 5 | IDN-02 | Group management | MUST | RELEASED | src/identity/registry.zig; src/identity/service.zig; src/api/routes/identity.zig; src/api/routes/tasks.zig; migrations/018_identity_group_members.sql
49 | 5 | IDN-03 | Role-based access | MUST | RELEASED | src/api/authorization.zig; src/api/routes/tasks.zig; src/tasks/store.zig
50 | 5 | IDN-04 | API token management | MUST | RELEASED | src/identity/service.zig; src/api/routes/identity.zig; src/api/middleware/auth.zig; migrations/019_idn04_api_token_management.sql
51 | 5 | SCH-01 | Durable timer creation | MUST | RELEASED | src/scheduler/store.zig; src/engine/transition.zig; src/engine/instance.zig; migrations/015_timers_status_constraint.sql; tests/bench/bench.zig
52 | 5 | SCH-02 | Timer polling | MUST | RELEASED | src/design/scheduler.md; src/scheduler/scheduler.zig
53 | 5 | SCH-03 | Timer cancellation | MUST | RELEASED | src/engine/instance.zig; tests/integration/sch02_timer_polling_test.zig
54 | 5 | SCH-04 | Escalation timer | MUST | RELEASED | src/scheduler/store.zig; src/tasks/store.zig; src/engine/instance.zig; src/scheduler/scheduler.zig; tests/integration/sch02_timer_polling_test.zig
55 | 5 | SCH-05 | Missed timer recovery | MUST | RELEASED | src/scheduler/scheduler.zig
56 | 5 | SCH-06 | Timer jitter | SHOULD | RELEASED | src/scheduler/scheduler.zig
57 | 5 | SCH-07 | Recurring timers | SHOULD | RELEASED | src/scheduler/recurrence.zig; src/scheduler/scheduler.zig; src/scheduler/store.zig; src/engine/instance.zig; migrations/016_timer_recurrence_fields.sql
58 | 6 | EXT-01 | Service task node type | MUST | RELEASED | src/definition/graph.zig; tests/unit/graph_node_attributes_test.zig; src/engine/service_task.zig; tests/unit/service_task_test.zig; src/bpm.zig; build.zig; tests/integration/ext01_service_task_test.zig; tests/integration/main_test.zig; tests/integration/obs05_dlq_test.zig
59 | 6 | EXT-02 | Webhook event dispatch | MUST | RELEASED | src/webhook/subscription_store.zig; src/webhook/dispatcher.zig; src/webhook/signing.zig; src/api/routes/webhooks.zig
60 | 6 | EXT-03 | Plugin interface | SHOULD | RELEASED | src/engine/plugin_interface.zig; src/engine/plugin_registry.zig; src/engine/instance.zig; src/bpm.zig; tests/unit/ext03_plugin_test.zig; build.zig; tests/integration/ext03_plugin_integration_test.zig; tests/integration/main_test.zig
61 | 6 | EXT-04 | Variable transformer | SHOULD | RELEASED | src/engine/plugin_interface.zig; src/engine/plugin_registry.zig; src/definition/graph.zig; src/definition/store.zig; src/definition/export_import.zig; src/definition/snapshot.zig; src/api/routes/definitions.zig; src/engine/transition.zig; src/engine/instance.zig; tests/unit/graph_edge_conditions_test.zig; tests/unit/test_engine_ee05.zig; tests/integration/ext04_variable_transformer_test.zig; tests/integration/main_test.zig
62 | 6 | EXT-05 | Sub-process support | SHOULD | RELEASED | src/engine/instance.zig; src/engine/transition.zig; src/definition/graph.zig; migrations/026_ext05_subprocess_links.sql; tests/unit/graph_node_attributes_test.zig; tests/integration/ext05_sub_process_support_test.zig; tests/integration/main_test.zig
63 | 6 | OBS-01 | Structured logging | MUST | RELEASED | src/obs/logger.zig; src/config.zig; src/main.zig; src/api/routes/health.zig; src/scheduler/scheduler.zig
64 | 6 | OBS-02 | Prometheus metrics | MUST | RELEASED | src/obs/metrics.zig; src/api/routes/metrics.zig; src/db/pool.zig; src/event_store/store.zig; src/engine/instance.zig
65 | 6 | OBS-03 | Audit log | MUST | RELEASED | migrations/020_obs03_audit_entries.sql; src/obs/audit.zig; src/api/routes/audit.zig; src/main.zig; src/bpm.zig; tests/integration/obs03_audit_log_test.zig; tests/integration/main_test.zig; build.zig
66 | 6 | OBS-04 | Instance timeline view | MUST | RELEASED | src/obs/timeline.zig; src/api/routes/instances.zig; src/api/authorization.zig; src/api/openapi/builder.zig; tests/unit/test_obs04_timeline.zig; build.zig; web/src/types/api.ts; web/src/api/instances.ts; web/src/hooks/useInstances.ts; web/src/pages/instances/InstanceDetailPage.tsx; web/src/pages/instances/timelineUtils.ts; web/src/pages/instances/timelineUtils.test.ts; web/src/api/identity.ts; tests/integration/obs04_timeline_test.zig; tests/integration/main_test.zig; src/main.zig; web/tests/e2e/obs04.timeline.e2e.spec.ts
67 | 6 | OBS-05 | Dead letter queue | MUST | RELEASED | src/dlq/store.zig; src/api/routes/dlq.zig; src/bpm.zig; src/main.zig; migrations/021_obs05_dead_letter_context.sql; tests/integration/obs05_dlq_test.zig; tests/integration/main_test.zig
68 | 6 | OBS-06 | Alerting hooks | SHOULD | RELEASED | src/obs/alerts.zig; src/main.zig; src/bpm.zig; migrations/022_obs06_alerting_state.sql; tests/integration/obs06_alerts_test.zig; tests/integration/main_test.zig
69 | 6.5 | ADP-01 | Tenant Column on Event Store | MUST | RELEASED | src/event_store/store.zig; src/obs/timeline.zig; migrations/027_adp01_event_store_tenant.sql; tests/integration/event_store_integration_test.zig
70 | 6.5 | ADP-02 | Tenant column on definition, instance, and audit tables | MUST | RELEASED | migrations/028_adp02_tenant_scope_persistence.sql; src/definition/store.zig; src/definition/snapshot.zig; src/definition/export_import.zig; src/engine/instance.zig; src/obs/audit.zig; tests/integration/adp02_tenant_scope_test.zig
71 | 6.5 | ADP-03 | Tenant context resolution on API | MUST | RELEASED | tests/integration/adp03_tenant_context_resolution_test.zig
72 | 6.5 | ADP-04 | Tenant binding for users | MUST | RELEASED | migrations/029_adp04_user_tenant_binding.sql; src/identity/registry.zig; src/identity/service.zig; src/api/routes/identity.zig; src/api/routes/tasks.zig; tests/integration/adp04_user_tenant_binding_test.zig; tests/integration/main_test.zig; tests/integration/idn02_group_management_test.zig
73 | 6.5 | ADP-04a | External identity linkage for users | MUST | RELEASED | migrations/030_adp04a_external_identity_linkage.sql; src/identity/registry.zig; src/identity/service.zig; tests/integration/adp04a_external_identity_linkage_test.zig
74 | 6.5 | ADP-04b | Tenant realm binding for OIDC foundations | MUST | RELEASED | migrations/031_adp04b_tenant_realm_binding.sql; src/identity/registry.zig; src/identity/service.zig; src/api/routes/identity.zig; tests/integration/adp04a_external_identity_linkage_test.zig; tests/integration/adp04b_tenant_realm_binding_test.zig; tests/integration/main_test.zig
75 | 6.5 | ADP-05 | Artifact hash reference on instance | MUST | RELEASED | migrations/032_adp05_instance_artifact_hash.sql; src/engine/instance.zig; src/engine/reconstruction.zig; tests/integration/adp05_instance_artifact_hash_test.zig; tests/integration/main_test.zig
76 | 6.5 | ADP-06 | Pipeline run correlation on audit and events | SHOULD | RELEASED | migrations/033_adp06_pipeline_run_correlation.sql; src/obs/audit.zig; src/event_store/store.zig; src/api/routes/audit.zig; src/api/routes/instances.zig; tests/integration/adp06_pipeline_run_correlation_test.zig; tests/integration/main_test.zig
77 | 6.5 | ADP-07 | Agent role and reserved usernames | MUST | RELEASED | src/api/middleware/auth.zig; src/identity/service.zig; src/api/routes/identity.zig; src/api/authorization.zig; migrations/034_adp07_agent_role_reserved_usernames.sql; tests/integration/adp07_agent_role_reserved_usernames_test.zig; tests/integration/main_test.zig
78 | 6.5 | ADP-08 | Service task catalog reference | MUST | RELEASED | src/engine/service_task.zig; src/engine/instance.zig; src/definition/graph.zig; tests/unit/service_task_test.zig; tests/unit/graph_node_attributes_test.zig; tests/integration/ext01_service_task_test.zig
79 | 6.5 | ADP-09 | Tamper-evident audit chain | MUST | RELEASED | migrations/035_adp09_tamper_evident_audit_chain.sql; tests/integration/adp09_tamper_evident_audit_chain_test.zig; tests/integration/main_test.zig
80 | 6.5 | ADP-10 | Agent IO capture audit | MUST | RELEASED | migrations/036_adp10_agent_io_capture_audit.sql; tests/integration/adp10_agent_io_capture_audit_test.zig; tests/integration/main_test.zig
81 | 6.5 | ADP-11 | Replay-safe retention policy | MUST | RELEASED | src/event_store/store.zig; migrations/037_adp11_replay_safe_retention_policy.sql; tests/integration/event_store_integration_test.zig
82 | 6.5 | ADP-12 | Default-tenant regression suite | MUST | RELEASED | build.zig; tests/integration/main_test.zig; tests/integration/adp12_default_tenant_regression_test.zig; tests/integration/support/regression_matrix.zig; tests/integration/support/response_canonicalizer.zig; tests/integration/support/migration_window_orchestrator.zig; tests/integration/support/report_writer.zig
83 | 6.5 | OIDC-01 | Pluggable provider interface | MUST | RELEASED | src/identity/provider/errors.zig; src/identity/provider/types.zig; src/identity/provider/interface.zig; src/identity/provider/manager.zig; src/identity/provider/mod.zig; src/identity/provider/adapters/keycloak/provider.zig; src/identity/provider/adapters/stub/provider.zig; src/api/middleware/auth.zig; src/api/api_mod.zig; src/identity/service.zig; tests/unit/test_api08_auth.zig; build.zig; tests/unit/test_oidc01_provider_boundary.zig; tests/unit/test_oidc01_provider_stub.zig
84 | 6.5 | OIDC-02 | Keycloak adapter | MUST | RELEASED | src/identity/provider/mod.zig; src/identity/provider/adapters/keycloak/config.zig; src/identity/provider/adapters/keycloak/urls.zig; src/identity/provider/adapters/keycloak/provider.zig; src/identity/provider/test_oidc02_keycloak_adapter.zig; tests/unit/test_oidc01_provider_boundary.zig; build.zig
85 | 6.5 | OIDC-03 | Configuration source | MUST | RELEASED | src/config/identity_provider.zig; src/identity/provider/bootstrap.zig; src/identity/provider/mod.zig; src/main.zig; build.zig
86 | 6.5 | OIDC-04 | Standards-compliance boundary | MUST | RELEASED | src/identity/provider/oidc/standards_verifier.zig; src/identity/provider/adapters/keycloak/provider.zig; src/identity/provider/test_oidc02_keycloak_adapter.zig
87 | 6.5 | OIDC-05 | Bearer token acceptance | MUST | RELEASED | src/api/middleware/auth.zig; src/identity/provider/manager.zig; tests/unit/test_api08_auth.zig; tests/unit/test_oidc01_provider_boundary.zig; tests/unit/test_oidc01_provider_stub.zig
88 | 6.5 | OIDC-06 | JWKS caching | MUST | RELEASED | src/identity/provider/oidc/jwks_cache.zig
89 | 6.5 | OIDC-07 | Claim validation | MUST | RELEASED | src/identity/provider/oidc/standards_verifier.zig
90 | 6.5 | OIDC-08 | Standard claim mapping | MUST | RELEASED | src/oidc/claim_mapping.zig
91 | 6.5 | OIDC-09 | JIT user creation | MUST | RELEASED | src/oidc/jit_provisioning.zig
92 | 6.5 | OIDC-10 | Attribute synchronisation | MUST | RELEASED | src/oidc/attribute_sync.zig (inferred)
93 | 6.5 | OIDC-11 | External user identity stability | MUST | RELEASED | src/oidc/identity_stability.zig
94 | 6.5 | OIDC-12 | Realm-tenant binding | MUST | RELEASED | src/oidc/realm_tenant_binding.zig
95 | 6.5 | OIDC-13 | Tenant claim source | MUST | RELEASED | src/oidc/tenant_claim_source.zig
96 | 6.5 | OIDC-14 | Realm provisioning via adapter | MUST | RELEASED | src/oidc/realm_provisioning.zig
97 | 6.5 | OIDC-15 | Realm deletion safety | MUST | RELEASED | src/oidc/realm_deletion.zig
98 | 6.5 | OIDC-16 | Full lifecycle API for agents | MUST | RELEASED | src/oidc/agent_lifecycle.zig
99 | 6.5 | OIDC-17 | Provisioning idempotency | MUST | RELEASED | src/oidc/agent_lifecycle.zig
100 | 6.5 | OIDC-18 | Provisioning transactional semantics | MUST | RELEASED | src/oidc/agent_lifecycle.zig
101 | 6.5 | OIDC-19 | Provisioning audit | MUST | RELEASED | src/oidc/agent_lifecycle.zig
102 | 6.5 | OIDC-20 | Service accounts for agents | MUST | RELEASED | src/oidc/agent_lifecycle.zig
103 | 6.5 | OIDC-21 | Agent token rotation | MUST | RELEASED | src/oidc/agent_lifecycle.zig
104 | 6.5 | OIDC-22 | Bootstrap agent identity | MUST | RELEASED | src/identity/provider/bootstrap.zig
105 | 6.5 | OIDC-23 | IDP federation support | MUST | RELEASED | src/oidc/agent_lifecycle.zig
106 | 6.5 | OIDC-24 | Federated user attribute mapping | SHOULD | RELEASED | src/oidc/agent_lifecycle.zig
107 | 6.5 | OIDC-25 | Provider health check | MUST | RELEASED | src/oidc/agent_lifecycle.zig
108 | 6.5 | OIDC-26 | Provider metrics | MUST | RELEASED | src/oidc/agent_lifecycle.zig
109 | 6.5 | OIDC-27 | Token verification performance | SHOULD | RELEASED | src/oidc/verification_benchmark.zig
110 | 6.5 | OIDC-28 | Local development realm | MUST | RELEASED | src/oidc/realm_seed.zig
111 | 6.5 | OIDC-29 | Realm seed as versioned artifact | MUST | RELEASED | src/oidc/realm_seed.zig
112 | 6.5 | OIDC-30 | Test token issuance helper | MUST | RELEASED | src/oidc/test_token_helper.zig
113 | 6.5 | OIDC-31 | End-to-end authentication test suite | MUST | RELEASED | src/oidc/test_token_helper.zig
114 | 6.5 | OIDC-32 | Agent test identities | MUST | RELEASED | src/oidc/test_token_helper.zig
115 | 6.5 | OIDC-33 | Coexistence period | MUST | RELEASED | src/oidc/coexistence_auth.zig
116 | 6.5 | OIDC-34 | Migration helper | SHOULD | RELEASED | src/oidc/migration_helper.zig
117 | 7 | DSL-01 | Grammar conformance | MUST | RELEASED | src/expr/error.zig; src/expr/ast.zig; src/expr/lexer.zig; src/expr/parser.zig; src/expr/mod.zig; build.zig
118 | 7 | DSL-02 | AST stability | MUST | RELEASED | src/expr/ast.zig
119 | 7 | DSL-03 | Error recovery | SHOULD | RELEASED | src/expr/parser.zig; src/expr/error.zig; src/expr/mod.zig; src/expr/lexer.zig; src/expr/ast.zig; tests/unit/expr_error_recovery_test.zig; build.zig
120 | 7 | DSL-04 | Supported types | MUST | RELEASED | src/expr/ast.zig; src/expr/mod.zig
121 | 7 | DSL-05 | Type coercion | MUST | RELEASED | src/expr/ast.zig; src/expr/mod.zig; src/expr/error.zig
122 | 7 | DSL-06 | Total evaluation | MUST | RELEASED | src/expr/evaluator.zig
123 | 7 | DSL-07 | Function whitelist | MUST | RELEASED | src/expr/lexer.zig; src/expr/mod.zig
124 | 7 | DSL-08 | Function purity | MUST | RELEASED | src/expr/mod.zig
125 | 7 | DSL-09 | Date built-ins | MUST | RELEASED | src/expr/mod.zig
126 | 7 | DSL-10 | Context resolution | MUST | RELEASED | src/expr/evaluator.zig
127 | 7 | DSL-11 | Dot path traversal | MUST | RELEASED | src/expr/evaluator.zig
128 | 7 | DSL-12 | Engine API | MUST | RELEASED | src/expr/mod.zig
129 | 7 | DSL-13 | Performance target | SHOULD | RELEASED | src/expr/benchmark.zig
130 | 8 | LUA-01 | LuaJIT integration | MUST | RELEASED | src/lua/luajit_bindings.zig
131 | 8 | LUA-02 | State isolation | MUST | RELEASED | src/lua/executor.zig
132 | 8 | LUA-03 | Stdlib restriction | MUST | RELEASED | src/lua/stdlib.zig
133 | 8 | LUA-04 | Bytecode loading disabled | MUST | RELEASED | src/lua/stdlib.zig; src/lua/executor.zig
134 | 8 | LUA-05 | Host API registration | MUST | RELEASED | src/lua/host_api/mod.zig
135 | 8 | LUA-06 | Capability check at call site | MUST | RELEASED | src/lua/capabilities.zig
136 | 8 | LUA-07 | Capability manifest validation | MUST | RELEASED | src/lua/manifest.zig
137 | 8 | LUA-08 | Instruction limit | MUST | RELEASED | src/lua/instruction_limiter.zig
138 | 8 | LUA-09 | Memory limit | MUST | RELEASED | src/lua/memory_limiter.zig
139 | 8 | LUA-10 | Wall clock timeout | MUST | RELEASED | src/lua/timeout.zig
140 | 8 | LUA-11 | Variable read/write | MUST | RELEASED | src/lua/executor.zig; src/lua/host_api/read_variable.zig; src/lua/host_api/write_variable.zig
141 | 8 | LUA-12 | Service call | MUST | RELEASED | src/lua/service_catalog.zig; src/lua/host_api/call_service.zig
142 | 8 | LUA-13 | Logging | MUST | RELEASED | src/lua/structured_logger.zig; src/lua/host_api/log.zig
143 | 8 | LUA-14 | Time source | MUST | RELEASED | src/lua/time_source.zig; src/lua/host_api/now.zig
144 | 8 | LUA-15 | Structured failure | MUST | RELEASED | src/lua/host_api/fail.zig; src/lua/events.zig
145 | 8 | LUA-16 | Runtime error capture | MUST | RELEASED | src/lua/errors.zig; src/lua/events.zig
146 | 8 | TM-01 | Platform-admin tenant list | MUST | RELEASED | src/api/routes/identity.zig; src/identity/service.zig; src/identity/registry.zig; web/src/pages/admin/tenants/TenantsPage.tsx; web/src/api/tenants.ts
147 | 8 | TM-02 | Navigation to tenant onboarding | MUST | RELEASED | web/src/pages/admin/tenants/TenantsPage.tsx
148 | 8 | TM-03 | Edit tenant mutable fields | MUST | RELEASED | src/api/routes/identity.zig; src/identity/service.zig; src/identity/registry.zig; web/src/pages/admin/tenants/EditTenantPage.tsx
149 | 8 | TM-04 | Deactivate tenant | MUST | RELEASED | src/api/routes/identity.zig; src/identity/service.zig; web/src/api/tenants.ts; web/src/pages/admin/tenants/TenantsPage.tsx
150 | 8 | TM-05 | Reactivate tenant | MUST | RELEASED | src/api/routes/identity.zig; src/identity/service.zig; web/src/api/tenants.ts; web/src/pages/admin/tenants/TenantsPage.tsx
151 | 9 | WASM-01 | Wasmtime integration | MUST | RELEASED | src/wasm/engine.zig; src/wasm/wasmtime_bindings.zig
152 | 9 | WASM-02 | Module ABI | MUST | RELEASED | src/wasm/instance.zig; src/wasm/executor.zig
153 | 9 | WASM-03 | Source compilation job | MUST | RELEASED | src/wasm/engine.zig
154 | 9 | WASM-04 | Compile caching | MUST | RELEASED | src/wasm/engine.zig
155 | 9 | WASM-05 | Build reproducibility | SHOULD | RELEASED | src/wasm/engine.zig
156 | 9 | WASM-06 | Import whitelist | MUST | RELEASED | src/wasm/capabilities.zig
157 | 9 | WASM-07 | No filesystem access | MUST | RELEASED | src/wasm/capabilities.zig
158 | 9 | WASM-08 | Memory isolation | MUST | RELEASED | src/wasm/instance.zig; src/wasm/memory.zig
159 | 9 | WASM-09 | Fuel-based execution limit | MUST | RELEASED | src/wasm/engine.zig; src/wasm/executor.zig
160 | 9 | WASM-10 | Memory cap | MUST | RELEASED | src/wasm/memory.zig
161 | 9 | WASM-11 | Wall clock timeout | MUST | RELEASED | src/wasm/timeout.zig
162 | 9 | WASM-12 | Parity with Lua host API | MUST | RELEASED | src/wasm/host_api/mod.zig
163 | 9 | WASM-13 | Instance pooling | SHOULD | RELEASED | src/wasm/pool.zig
164 | 9 | WASM-14 | Hot reload | MUST | RELEASED | src/wasm/module_registry.zig
165 | 10 | REPO-01 | Content addressing | MUST | RELEASED | src/repository/canonicaliser.zig; src/repository/artifacts.zig
166 | 10 | REPO-02 | Immutability | MUST | RELEASED | src/repository/artifacts.zig
167 | 10 | REPO-03 | Versioning | MUST | RELEASED | src/repository/artifacts.zig
168 | 10 | REPO-04 | Canonical serialisation | MUST | RELEASED | src/repository/canonicaliser.zig
169 | 10 | REPO-05 | Form schema indexing | MUST | RELEASED | src/repository/schemas.zig
170 | 10 | REPO-06 | Event type registry | MUST | RELEASED | src/repository/schemas.zig
171 | 10 | REPO-07 | Service catalog | MUST | RELEASED | src/repository/service_catalog.zig
172 | 10 | REPO-08 | Atomic activation | MUST | RELEASED | src/repository/activation.zig
173 | 10 | REPO-09 | Per-tenant activation | MUST | RELEASED | src/repository/activation.zig
174 | 10 | REPO-10 | Activation history | MUST | RELEASED | src/repository/activation.zig
175 | 10 | REPO-11 | Create artifact | MUST | RELEASED | src/api/routes/repository.zig; src/repository/artifacts.zig
176 | 10 | REPO-12 | List versions | MUST | RELEASED | src/api/routes/repository.zig; src/repository/artifacts.zig
177 | 10 | REPO-13 | Tenant activations | MUST | RELEASED | src/api/routes/repository.zig; src/repository/activation.zig
178 | 10 | REPO-14 | Bulk bundle operations | SHOULD | RELEASED | src/repository/activation.zig
179 | 10 | XC-01 | Trace propagation | MUST | RELEASED | src/api/trace_context.zig; src/api/middleware/trace.zig; src/obs/audit.zig; src/api/errors.zig
180 | 10 | XC-02 | Audit immutability | MUST | RELEASED | src/obs/audit.zig
181 | 10 | XC-03 | Configuration in repository | MUST | RELEASED | src/config/loader.zig; src/repository/activation.zig
182 | 10 | XC-04 | Kernel determinism | MUST | RELEASED | src/engine/transition.zig; src/event_store/store.zig; src/scheduler/scheduler.zig
183 | 10 | XC-05 | Deterministic replay for non-LLM tiers | SHOULD | RELEASED | src/engine/transition.zig; src/event_store/store.zig
184 | 10 | XC-06 | Backwards compatibility | MUST | RELEASED | src/db/migrations.zig; src/definition/store.zig
185 | 11 | SIM-01 | Simulation tenant | MUST | RELEASED | tests/integration/helpers.zig; tests/integration/sim01_04_simulation_mode_test.zig; tests/integration/xc04_kernel_determinism_test.zig; tests/integration/main_test.zig; tests/integration/stage11_sim_xc04_aggregate_test.zig; tests/integration/oidc31_end_to_end_auth_suite_test.zig; tests/integration/oidc35_onboarding_test.zig; src/simulation/types.zig; src/simulation/context.zig; src/simulation/time_source.zig; src/simulation/uuid_source.zig; src/simulation/mock_catalog.zig; src/simulation/service_interceptor.zig; src/simulation/tenant_store.zig; src/simulation/runtime.zig; src/simulation/mod.zig; src/lua/host_api/now.zig; src/lua/host_api/call_service.zig; src/bpm.zig; src/db/migrations.zig; src/tools/migrate.zig
186 | 11 | SIM-02 | Service mocking | MUST | RELEASED | tests/integration/helpers.zig; tests/integration/sim01_04_simulation_mode_test.zig; tests/integration/xc04_kernel_determinism_test.zig; tests/integration/main_test.zig; tests/integration/stage11_sim_xc04_aggregate_test.zig; tests/integration/oidc31_end_to_end_auth_suite_test.zig; tests/integration/oidc35_onboarding_test.zig; src/simulation/types.zig; src/simulation/context.zig; src/simulation/time_source.zig; src/simulation/uuid_source.zig; src/simulation/mock_catalog.zig; src/simulation/service_interceptor.zig; src/simulation/tenant_store.zig; src/simulation/runtime.zig; src/simulation/mod.zig; src/lua/host_api/now.zig; src/lua/host_api/call_service.zig; src/bpm.zig; src/db/migrations.zig; src/tools/migrate.zig
187 | 11 | SIM-03 | Time control | MUST | RELEASED | tests/integration/helpers.zig; tests/integration/sim01_04_simulation_mode_test.zig; tests/integration/xc04_kernel_determinism_test.zig; tests/integration/main_test.zig; tests/integration/stage11_sim_xc04_aggregate_test.zig; tests/integration/oidc31_end_to_end_auth_suite_test.zig; tests/integration/oidc35_onboarding_test.zig; src/simulation/types.zig; src/simulation/context.zig; src/simulation/time_source.zig; src/simulation/uuid_source.zig; src/simulation/mock_catalog.zig; src/simulation/service_interceptor.zig; src/simulation/tenant_store.zig; src/simulation/runtime.zig; src/simulation/mod.zig; src/lua/host_api/now.zig; src/lua/host_api/call_service.zig; src/bpm.zig; src/db/migrations.zig; src/tools/migrate.zig
188 | 11 | SIM-04 | Deterministic UUIDs | MUST | RELEASED | tests/integration/helpers.zig; tests/integration/sim01_04_simulation_mode_test.zig; tests/integration/xc04_kernel_determinism_test.zig; tests/integration/main_test.zig; tests/integration/stage11_sim_xc04_aggregate_test.zig; tests/integration/oidc31_end_to_end_auth_suite_test.zig; tests/integration/oidc35_onboarding_test.zig; src/simulation/types.zig; src/simulation/context.zig; src/simulation/time_source.zig; src/simulation/uuid_source.zig; src/simulation/mock_catalog.zig; src/simulation/service_interceptor.zig; src/simulation/tenant_store.zig; src/simulation/runtime.zig; src/simulation/mod.zig; src/lua/host_api/now.zig; src/lua/host_api/call_service.zig; src/bpm.zig; src/db/migrations.zig; src/tools/migrate.zig
189 | 11 | SIM-05 | Scenario schema | MUST | RELEASED | tests/integration/main_test.zig; tests/integration/sim05_08_scenario_runner_test.zig; tests/integration/helpers.zig; src/simulation/mod.zig; src/main.zig; src/bpm.zig
190 | 11 | SIM-06 | Assertion vocabulary | MUST | RELEASED | tests/integration/main_test.zig; tests/integration/sim05_08_scenario_runner_test.zig; tests/integration/helpers.zig; src/simulation/mod.zig; src/main.zig; src/bpm.zig
191 | 11 | SIM-07 | Scenario runner | MUST | RELEASED | tests/integration/main_test.zig; tests/integration/sim05_08_scenario_runner_test.zig; tests/integration/helpers.zig; src/simulation/mod.zig; src/main.zig; src/bpm.zig
192 | 11 | SIM-08 | Batch execution | MUST | RELEASED | tests/integration/main_test.zig; tests/integration/sim05_08_scenario_runner_test.zig; tests/integration/helpers.zig; src/simulation/mod.zig; src/main.zig; src/bpm.zig
193 | 11 | SIM-09 | Test result storage | MUST | RELEASED | src/simulation/scenario_runner.zig; src/api/routes/simulation_test.zig
194 | 11 | SIM-10 | Failure diagnostics | MUST | RELEASED | src/simulation/scenario_runner.zig; src/simulation/types.zig; src/api/routes/simulation_test.zig
195 | 12 | TNT-01 | Business tables migrated to per-tenant schemas | MUST | RELEASED | WF02-tnt-batch1-20260609
196 | 12 | TNT-02 | Migration runner enforces search_path isolation | MUST | RELEASED | WF02-tnt-batch1-20260609
197 | 12 | TNT-03 | Connection pool sets search_path per tenant on checkout | MUST | RELEASED | WF02-tnt-batch1-20260609
198 | 12 | TNT-04 | Platform startup audits public schema | MUST | RELEASED | WF02-tnt-batch1-20260609
199 | 12 | TNT-05 |  | MUST | RELEASED | WF02-tnt-batch2-20260609
200 | 12 | TNT-06 |  | MUST | RELEASED | WF02-tnt-batch2-20260609
201 | 12 | TNT-07 |  | MUST | RELEASED | WF02-tnt-batch2-20260609
202 | 13 | SVC-01 | Service catalog entries carry a scope and owner tenant | MUST | RELEASED | WF02-svc-batch1-20260610
203 | 13 | SVC-02 | Plugin handlers declare scope and optional owner tenant at registration | MUST | RELEASED | WF02-svc-batch1-20260610
204 | 13 | SVC-03 | Definition activation validates service and plugin availability | MUST | RELEASED | WF02-svc-batch1-20260610
205 | 13 | SVC-04 | Admin UI and API for service catalog scope management | MUST | RELEASED | WF02-svc-batch1-20260610
206 | 14 | ENV-01 | Tenant carries a type field distinguishing production from test | MUST | RELEASED | WF02-env-batch1-20260610
207 | 14 | ENV-02 | Test tenant is fully isolated from its paired production tenant | MUST | RELEASED | WF02-env-batch1-20260610
208 | 14 | ENV-03 | Process definition promotion from test tenant to production tenant | MUST | RELEASED | WF02-env-batch1-20260610
209 | 14 | ENV-05 | Test tenant lifecycle management | SHOULD | RELEASED | WF02-env-batch1-20260610
210 | F1 | SH-01 | Authenticated shell | MUST | RELEASED | web/src/components/layout/AppShell.tsx
211 | F1 | SH-02 | Navigation | MUST | RELEASED | web/src/components/layout/AppShell.tsx
212 | F1 | SH-03 | Login page | MUST | RELEASED | web/src/pages/LoginPage.tsx
213 | F1 | SH-04 | Token storage | MUST | RELEASED | web/src/auth/tokenUtils.ts; web/src/auth/AuthProvider.tsx
214 | F1 | SH-05 | Session expiry | MUST | RELEASED | web/src/auth/tokenUtils.ts; web/src/auth/OidcManager.ts
215 | F1 | SH-06 | Role-aware routing | MUST | RELEASED | web/src/router.tsx; web/src/auth/ProtectedRoute.tsx
216 | F1 | SH-07 | Global error boundary | MUST | RELEASED | web/src/components/layout/ErrorBoundary.tsx
217 | F2 | PD-UI-01 | Definition list page | MUST | RELEASED | web/src/pages/definitions/DefinitionListPage.tsx
218 | F2 | PD-UI-02 | Create definition | MUST | RELEASED | web/src/pages/definitions/DefinitionListPage.tsx; web/src/pages/definitions/DefinitionEditorPage.tsx
219 | F2 | PD-UI-03 | Canvas | MUST | RELEASED | web/src/components/canvas/ProcessCanvas.tsx
220 | F2 | PD-UI-04 | Add / delete node | MUST | RELEASED | web/src/components/canvas/ProcessCanvas.tsx; web/src/components/canvas/NodePalette.tsx
221 | F2 | PD-UI-05 | Node property panel | MUST | RELEASED | web/src/components/canvas/PropertyPanel.tsx
222 | F2 | PD-UI-06 | Add / delete edge | MUST | RELEASED | web/src/components/canvas/ProcessCanvas.tsx; web/src/components/canvas/edges/ConditionEdge.tsx
223 | F2 | PD-UI-07 | CEL expression editor | MUST | RELEASED | web/src/components/canvas/CelExpressionEditor.tsx
224 | F2 | PD-UI-08 | Save definition | MUST | RELEASED | web/src/pages/definitions/DefinitionEditorPage.tsx; web/src/api/definitions.ts
225 | F2 | PD-UI-09 | Validation feedback | MUST | RELEASED | web/src/components/canvas/ValidationSummaryBar.tsx
226 | F2 | PD-UI-10 | Version list | MUST | RELEASED | web/src/pages/definitions/DefinitionListPage.tsx
227 | F2 | PD-UI-11 | Activate version | MUST | RELEASED | web/src/pages/definitions/DefinitionListPage.tsx
228 | F2 | PD-UI-12 | Deprecate version | MUST | RELEASED | web/src/pages/definitions/DefinitionListPage.tsx
229 | F2 | PD-UI-13 | Definition export | SHOULD | RELEASED | web/src/pages/definitions/DefinitionListPage.tsx; web/src/api/definitions.ts
230 | F2 | PD-UI-14 | Definition import | SHOULD | RELEASED | web/src/pages/definitions/DefinitionListPage.tsx; web/src/api/definitions.ts
231 | F2 | PD-UI-15 | Read-only canvas | MUST | RELEASED | web/src/pages/definitions/DefinitionEditorPage.tsx; web/src/components/canvas/ProcessCanvas.tsx
232 | F2 | PD-UI-16 | Diff view | SHOULD | RELEASED | web/src/components/ui/JsonDiffView.tsx
233 | F2 | PD-UI-17 | Canvas keyboard shortcuts | SHOULD | RELEASED | web/src/components/canvas/ProcessCanvas.tsx
234 | F2 | PD-UI-18 | Auto-layout | COULD | RELEASED | web/src/components/canvas/ProcessCanvas.tsx
235 | F2 | PD-UI-19 | Mini-map | COULD | RELEASED | web/src/components/canvas/ProcessCanvas.tsx
236 | F3 | IN-UI-01 | Instance board | MUST | RELEASED | web/src/pages/instances/InstanceBoardPage.tsx
237 | F3 | IN-UI-02 | Instance filters | MUST | RELEASED | web/src/pages/instances/InstanceBoardPage.tsx
238 | F3 | IN-UI-03 | Start instance | MUST | RELEASED | web/src/pages/instances/InstanceBoardPage.tsx
239 | F3 | IN-UI-04 | Instance detail view | MUST | RELEASED | web/src/pages/instances/InstanceDetailPage.tsx
240 | F3 | IN-UI-05 | Event history tab | MUST | RELEASED | web/src/pages/instances/InstanceDetailPage.tsx; web/src/components/instances/EventHistoryPanel.tsx; web/src/components/instances/EventJsonExpandable.tsx
241 | F3 | IN-UI-06 | Timeline tab | MUST | RELEASED | web/src/pages/instances/InstanceDetailPage.tsx; web/src/components/instances/TimelineFeed.tsx; web/src/components/instances/ActorAvatar.tsx; src/obs/timeline.zig
242 | F3 | IN-UI-07 | Cancel instance | MUST | RELEASED | web/src/pages/instances/InstanceDetailPage.tsx; web/src/components/instances/CancelInstanceDialog.tsx; web/src/hooks/useInstances.ts
243 | F3 | IN-UI-08 | Auto-refresh | SHOULD | RELEASED | web/src/hooks/usePolling.ts; web/src/pages/instances/InstanceBoardPage.tsx; web/src/pages/instances/InstanceDetailPage.tsx
244 | F3 | IN-UI-09 | Active token visualisation | SHOULD | RELEASED | web/src/components/instances/ProcessGraphWithTokens.tsx
245 | F3 | IN-UI-10 | History scrubber | SHOULD | RELEASED | web/src/components/instances/HistoryScrubber.tsx
246 | F4 | TK-UI-01 | Task inbox display and filtering | MUST | RELEASED | web/src/pages/tasks/TaskInboxPage.tsx; web/src/api/tasks.ts; web/src/hooks/useTasks.ts
247 | F4 | TK-UI-02 | Task detail panel display | MUST | RELEASED | web/src/pages/tasks/TaskInboxPage.tsx; web/src/components/tasks/TaskDetailPanel.tsx
248 | F4 | TK-UI-03 | Dynamic form schema rendering | MUST | RELEASED | web/src/components/tasks/TaskDetailPanel.tsx; web/src/components/tasks/DynamicForm.tsx
249 | F4 | TK-UI-04 | Task completion | MUST | RELEASED | web/src/hooks/useTasks.ts; src/tasks/store.zig; src/api/routes/tasks.zig
250 | F4 | TK-UI-05 | Claim group-assigned tasks | MUST | RELEASED | web/src/hooks/useTasks.ts; web/src/api/tasks.ts; src/api/routes/tasks.zig
251 | F4 | TK-UI-06 | Reassign tasks (operator) | MUST | RELEASED | web/src/hooks/useTasks.ts; web/src/components/tasks/ReassignDialog.tsx; src/api/routes/tasks.zig
252 | F4 | TK-UI-07 | Sort and free-text search | SHOULD | RELEASED | web/src/pages/tasks/TaskInboxPage.tsx; web/src/hooks/useTasks.ts
253 | F4 | TK-UI-08 | Navigation badge count | SHOULD | RELEASED | web/src/components/layout/Sidebar.tsx; web/src/hooks/useTasks.ts
254 | F4 | TK-UI-09 | Escalation indicator | SHOULD | RELEASED | web/src/pages/tasks/TaskInboxPage.tsx; web/src/components/tasks/TaskDetailPanel.tsx
255 | F4 | TK-UI-10 | Mobile responsive layout | MUST | RELEASED | web/src/pages/tasks/TaskInboxPage.tsx; web/src/components/tasks/TaskDetailPanel.tsx
256 | F5 | ADM-UI-01 | User list | MUST | RELEASED | web/src/pages/admin/users/UsersPage.tsx; web/src/pages/admin/UsersPage.tsx
257 | F5 | ADM-UI-02 | Create user | MUST | RELEASED | web/src/pages/admin/users/UsersPage.tsx
258 | F5 | ADM-UI-03 | Edit user | MUST | RELEASED | web/src/pages/admin/UserDetailPage.tsx
259 | F5 | ADM-UI-04 | Deactivate user | MUST | RELEASED | web/src/pages/admin/UserDetailPage.tsx
260 | F5 | ADM-UI-05 | Group management | MUST | RELEASED | web/src/pages/admin/GroupsPage.tsx
261 | F5 | ADM-UI-06 | Token list | MUST | RELEASED | web/src/pages/admin/TokensPage.tsx
262 | F5 | ADM-UI-07 | Issue token | MUST | RELEASED | web/src/pages/admin/TokensPage.tsx
263 | F5 | ADM-UI-08 | Revoke token | MUST | RELEASED | web/src/pages/admin/TokensPage.tsx
264 | F5 | ADM-UI-09 | Health dashboard | MUST | RELEASED | web/src/pages/admin/HealthDashboardPage.tsx
265 | F5 | ADM-UI-10 | Metrics viewer | SHOULD | RELEASED | web/src/pages/admin/MetricsPage.tsx
266 | F5 | ADM-UI-11 | Audit log viewer | MUST | RELEASED | web/src/pages/admin/AuditLogPage.tsx
267 | F6 | DLQ-UI-01 | DLQ list | MUST | RELEASED | web/src/pages/dlq/DlqItemsPage.tsx
268 | F6 | DLQ-UI-02 | DLQ item detail | MUST | RELEASED | web/src/pages/dlq/DlqPage.tsx
269 | F6 | DLQ-UI-03 | Retry action | MUST | RELEASED | web/src/pages/dlq/DlqPage.tsx
270 | F6 | DLQ-UI-04 | Discard action | MUST | RELEASED | web/src/pages/dlq/DlqPage.tsx
271 | F6 | DLQ-UI-05 | DLQ nav badge | MUST | RELEASED | web/src/components/layout/AppShell.tsx
272 | F6 | WH-UI-01 | Webhook list | MUST | RELEASED | web/src/pages/dlq/WebhooksPage.tsx
273 | F6 | WH-UI-02 | Webhook pause/resume | MUST | RELEASED | web/src/pages/dlq/WebhooksPage.tsx
274 | F6 | WH-UI-03 | Webhook delete | MUST | RELEASED | web/src/pages/dlq/WebhooksPage.tsx
275 | F6 | WH-UI-04 | Delivery log | SHOULD | RELEASED | web/src/components/webhooks/WebhookSubscriptionDetailPanel.tsx; web/src/components/webhooks/WebhookDeliveryAttemptsTable.tsx
276 | F7 | ONB-UI-01 | Register Tenant entry point | MUST | RELEASED | web/src/components/layout/AppShell.tsx
277 | F7 | ONB-UI-02 | Tenant registration form | MUST | RELEASED | web/src/pages/admin/onboarding/RegisterTenantPage.tsx; web/src/api/onboarding.ts
278 | F7 | ONB-UI-03 | Onboarding progress display | MUST | RELEASED | web/src/pages/admin/onboarding/OnboardingProgressPage.tsx
279 | F7 | ONB-UI-04 | Onboarding result screen | MUST | RELEASED | web/src/pages/admin/onboarding/OnboardingResultPage.tsx
280 | scheduler | ISS-301 | Remove redundant advisory lock from timer-claim path | MUST | RELEASED | src/scheduler/timer.zig
281 | scheduler | ISS-302 | Guard startup missed-timer sweep with advisory lock | MUST | RELEASED | src/scheduler/timer.zig
282 | scheduler | ISS-303 | Timer firing exhaustion routing to DLQ | MUST | RELEASED | src/scheduler/timer.zig; migrations/092_iss303_timer_fire_error_count.sql
283 | Expansion | EXP-101 |  | P1 | RELEASED
284 | Expansion | EXP-102 | Wire src/expr into transition.zig as production gateway condition evaluator; retire vendor/cel | P1 | RELEASED | src/engine/transition.zig; src/expr/
285 | Expansion | EXP-103 | Persist instance_waits descriptors atomically on timer/task arm and resolve | P1 | RELEASED | src/engine/instance.zig; migrations/093_exp103_instance_waits.sql
286 | Expansion | EXP-201 | Entity definition format + Repository artifact | P0 | RELEASED | src/entities/definition.zig; src/entities/validator.zig; src/entities/mod.zig; src/repository/canonicaliser.zig; migrations/094_entity_subsystem.sql
287 | Expansion | EXP-202 | Entity command API -> event family | P0 | RELEASED | src/entities/events.zig; src/entities/commands.zig; src/entities/projector.zig; src/api/routes/entities.zig; migrations/094_entity_subsystem.sql
288 | Epic 3 | EXP-301 | Effects outbox + worker polling + retry/backoff | P1 | RELEASED | src/effects/
289 | Epic 3 | EXP-302 | SERVICE_TASK migrated to async effect emit-and-wait | P1 | RELEASED | src/engine/service_task.zig
290 | Epic 3 | EXP-303 | Stub effects executor for sandbox/deterministic tests | P1 | RELEASED | src/effects/stub.zig
291 | Epic 4 | EXP-401 | Compensation handler + error-boundary constructs | P1 | RELEASED | src/engine/
292 | Epic 4 | EXP-402 | Restore reconciliation + re-arm waits (restored_orphan) | P1 | RELEASED | src/engine/
293 | Epic 5 | ISS-501 | Resolve read/write authority from storage_mode | P0 | IMPLEMENTED | src/api/tenant_context.zig; src/db/pool.zig
294 | Epic 5 | ISS-502 | SPT cutover transaction flips storage_mode after verified copy | P0 | IMPLEMENTED | src/admin/tenant_migration.zig
295 | Epic 5 | ISS-503 | Remove legacy tenant_id/RLS predicates (SPT-03) | P1 | IMPLEMENTED | migrations/GBL-084_rls_removal.sql; src/db/pool.zig
296 | Epic 5 | ISS-504 | Reconcile schema + per-tenant migration tracking (SPT-04) | P2 | IMPLEMENTED | src/db/provisioning.zig; src/db/migrations.zig
297 | Epic 6 | EXP-601 | Central tier->quota enforcement middleware | P1 | RELEASED | src/api/middleware/quota_enforcement.zig
298 | correctness | ISS-101 | timers.status CHECK constraint must include FAILED value | MUST | RELEASED | migrations/081_iss101_timers_failed_status.sql; tests/integration/iss101_timers_failed_status_test.zig
299 | correctness | ISS-102 | Add tasks.claimed_by column and real claim path | MUST | RELEASED | migrations/082_iss102_tasks_claimed_by.sql; src/tasks/store.zig; src/api/routes/tasks.zig; tests/integration/iss102_claim_test.zig
300 | correctness | ISS-105 | Persist new token model ({token_id,node_id} + join_counters) | MUST | RELEASED | migrations/083_instances_token_model.sql; migrations/088_iss105_instances_token_model_backfill.sql; src/engine/instance.zig; src/design/iss105_token_model_schema.md
301 | correctness | ISS-106 | Formalize webhook_deliveries outbox table | MUST | RELEASED | migrations/085_iss106_webhook_deliveries_outbox.sql; tests/integration/iss106_webhook_outbox_test.zig
302 | correctness | ISS-107 | Add public.tenants.storage_mode flag for SPT coexistence | MUST | RELEASED | migrations/086_iss107_tenant_storage_mode.sql; src/db/provisioning.zig; tests/integration/iss107_tenant_storage_mode_test.zig
303 | correctness | ISS-201 | Make transition() return TransitionResult{state, emitted_events} | MUST | RELEASED | src/engine/transition.zig; src/engine/instance.zig; src/engine/reconstruction.zig
304 | correctness | ISS-202 | Two-phase all-or-nothing variable merge | MUST | TESTED | src/engine/instance.zig; tests/unit/test_ee09_merge_variables.zig; tests/integration/ee09_merge_variables_test.zig; tests/integration/iss202_merge_atomicity_test.zig
305 | correctness | ISS-203 | Deterministic idempotency keys for engine-emitted cascade events | MUST | RELEASED | src/engine/transition.zig; src/engine/instance.zig; src/engine/reconstruction.zig; src/event_store/store.zig; tests/unit/service_task_test.zig; tests/unit/test_engine_apply.zig; tests/unit/test_engine_ee05.zig; tests/unit/test_ee07_parallel_join.zig; tests/integration/iss203_idempotency_keys_test.zig
306 | Schema-Per-Tenant Migration | SPT-01 | Schema-per-tenant provisioning infrastructure | MUST | RELEASED | migrations/060_schema_per_tenant_bootstrap.sql; src/db/migrations.zig; src/db/pool.zig; src/db/provisioning.zig
307 | Schema-Per-Tenant Migration | SPT-02 | Data migration — copy rows into tenant schemas and remove RLS | MUST | PENDING
308 | Schema-Per-Tenant Migration | SPT-03 | Remove legacy bpm.tenant_id session variable and tenant_id predicates | MUST | PENDING
309 | Schema-Per-Tenant Migration | SPT-04 | Test suite update and ADP-12 regression | MUST | PENDING
310 | UAT Tenant URL | UAT-TM-01 | Parameterise Keycloak token helper realm | MUST | RELEASED | web/tests/e2e/pipeline.ts
311 | UAT Tenant URL | UAT-TM-02 | Resolve tenant context from company slug | MUST | RELEASED | web/tests/e2e/pipeline.ts
312 | UAT Tenant URL | UAT-TM-03 | UAT runner step 2.5 tenant context resolution | MUST | RELEASED | docs/agents/UAT_RUNNER.md
313 | UAT Tenant URL | UAT-TM-04 | Scenario schema company_id auto-resolution guidance | MUST | RELEASED | docs/agents/uat-scenario-schema.md
314 | None | ISS-204 |  |  | RELEASED | feature/WF02-iss204-206-20260611
315 | None | ISS-206 |  |  | RELEASED | feature/WF02-iss204-206-20260611

## Action Items
Open tracked items + Borrowing backlog (what is left to do)
Track/Phase | ID | Title | Priority | Status | Note
(open – existing) | ISS-501 | Resolve read/write authority from storage_mode | P0 | IMPLEMENTED | Schema-per-tenant cutover / correctness — finish & release
(open – existing) | ISS-502 | SPT cutover transaction flips storage_mode after verified copy | P0 | IMPLEMENTED | Schema-per-tenant cutover / correctness — finish & release
(open – existing) | ISS-503 | Remove legacy tenant_id/RLS predicates (SPT-03) | P1 | IMPLEMENTED | Schema-per-tenant cutover / correctness — finish & release
(open – existing) | ISS-504 | Reconcile schema + per-tenant migration tracking (SPT-04) | P2 | IMPLEMENTED | Schema-per-tenant cutover / correctness — finish & release
(open – existing) | ISS-202 | Two-phase all-or-nothing variable merge | MUST | TESTED | Schema-per-tenant cutover / correctness — finish & release
(open – existing) | SPT-02 | Data migration — copy rows into tenant schemas and remove RLS | MUST | PENDING | Schema-per-tenant cutover / correctness — finish & release
(open – existing) | SPT-03 | Remove legacy bpm.tenant_id session variable and tenant_id predicates | MUST | PENDING | Schema-per-tenant cutover / correctness — finish & release
(open – existing) | SPT-04 | Test suite update and ADP-12 regression | MUST | PENDING | Schema-per-tenant cutover / correctness — finish & release
A0 | BRW-OPS-1 | Stated scale anchor | MUST | NOT STARTED | Doc; gates engine caps
A0 | BRW-OPS-3 | Written sandbox threat model (Lua+Wasm+agent) | MUST | NOT STARTED | Doc; gates agent-authored prod code
A1 | BRW-ENG-1 | Formalized per-node retry policy + deterministic budget | MUST | VERIFY | Partly via DLQ/EXP-301 — verify
A1 | BRW-ENG-2 | Failed-instance lifecycle (out-of-band log, retry/cancel) | MUST | VERIFY | Verify vs current engine/DLQ
A1 | BRW-ENG-3 | Parallel-branch failure isolation (join blocks) | MUST | VERIFY | Verify vs current engine
A2 | BRW-ENG-4 | Compensation + error-boundary constructs | SHOULD | LIKELY DONE | EXP-401 RELEASED 6/13 — verify parity
A2 | BRW-ENG-5 | Restore reconciliation + instance_waits | SHOULD | LIKELY DONE | EXP-402/103 RELEASED — verify parity
A3 | BRW-SEC-1 | HMAC ingress key rotation w/ grace window | SHOULD | NOT STARTED | Extend src/secrets (base shipped)
A3 | BRW-EFX-1 | Async-effects coverage + per-endpoint circuit breaker | SHOULD | MOSTLY DONE | EXP-301/302/303 shipped; breaker [S] new
A3 | BRW-SAGA-1 | Extract generic minimal saga runner | SHOULD | NOT STARTED | Refactor onboarding routes
A3 | BRW-OPS-2 | Tier->quota model coverage | SHOULD | MOSTLY DONE | EXP-601 shipped; verify dimensions
A4 | BRW-OPS-4 | Ephemeral throwaway-sandbox tier (agent loop) | COULD | NOT STARTED | Conditional on agent-authoring roadmap
M1 | BRW-MOB-1 | Generic definition-interpreter mobile app | MUST | NOT STARTED | Greenfield Flutter — largest gap
M2 | BRW-MOB-2 | Tenant bootstrap (slug->config->OIDC PKCE) | MUST | NOT STARTED | Needs tenant-config endpoint (verify)
M3 | BRW-MOB-5 | On-device security (secure token storage) | MUST | NOT STARTED
M4 | BRW-MOB-3 | Offline definition cache + delta sync + pinning | MUST | NOT STARTED | May need /definitions/delta endpoint
M5 | BRW-MOB-4 | Generic renderers + six mandatory states | MUST | NOT STARTED | Reuses SPA contracts
M6 | BRW-MOB-6 | API client (auth/refresh/retry/typed errors) | SHOULD | NOT STARTED
M7 | BRW-MOB-7 | i18n (reuse SPA locale policy) | SHOULD | NOT STARTED
M8 | BRW-MOB-8 | Enforce v1 scope boundary (online-first) | MUST | NOT STARTED | Defer offline writes